## CBG Workplan Blank Template
MMF Capacity Building Grant Workplan
Project Description:______________________________________________________________
Name of Applicant _____________________________________________________________
Activity/Tactics | Responsibility | Output (Product) | Time Line | Consultant Time

## SAMPLE CBG Workplan
Sample Capacity Building Workplan
Title: Fundraising project
Activity/Tactics | Responsibility | Output (Product) | Time Line | Consultant Time
Define the unique attributes of the organization and the stakeholders whose input would be valuable in this process. | Staff leaders | Written summary of a meeting involving these individuals | 2016-06-01 | 4 hours @ $125
Board leaders
Analyze all cultivation and solicitation activities from the past five years and the income & expenses and staff & Board roles for each activity. | Consultant | Results included in preliminary report | 2016-06-01 | 10 hours @ $125
(staff time required to assemble information)
Analyze current donor database. | Consultant | Results included in preliminary report | 2016-06-01 | 8 hours @ $125
(staff time required to pull reports)
Prepare and administer research instrument(s) to gain feedback from current donors. | Consultant | Results included in preliminary report | 2016-07-01 | 18 hours @ $75
Conduct research to identify new prospects. | Consultant | Results included in preliminary report | 2016-07-01 | 8 hours @ $75
Prepare preliminary report of findings and recommendations. | Consultant | Written report that is also presented to Board & staff leadership for discussion and adoption of recommendations | 2016-08-01 | 10 hours @ $125
(Board & Staff leadership time required for review of report and a meeting)
Fund Development Plan prepared and discussed with staff leadership. | Consultant, ED Staff Leadership | Written fund development plan includes information from preliminary report and specific activities, timeline, budget, staffing & volunteer support needed for implementation | 2016-09-01 | 16 hours @ $125
Adoption of fund development plan. | Board of Directors | Positive vote for implementation | 2016-10-01 | n/a
Ongoing coaching to executive director, board and staff. | Consultant, ED Staff Leadership | Ability to implement plan | Oct – Dec 2016 | 30 hours @ $125
SAMPLE
SAMPLE